## Slide 1
DEVELOPMENT PROGRESS REPORT
ParSU e-Feedback System
Complaint & Feedback Management Platform for Partido State University
50% COMPLETE
Prepared for: Project Stakeholders & Review Panel Reporting period: Development Phase — Mid-Cycle Checkpoint Date: August 18, 2026

## Slide 2
Agenda
01
Project Overview
Purpose, scope, and target users of the platform
02
Progress at a Glance
Overall completion status and delivery snapshot
03
Completed Modules
Features that are built, tested, and functioning
04
Work In Progress & Remaining
What is left before full delivery
05
Technical Foundation
Architecture, stack, and data model
06
Timeline & Next Steps
Path to completion and upcoming milestones
ParSU e-Feedback System | Development Progress Report
2

## Slide 3
Project Overview
ParSU e-Feedback is a web-based complaint and feedback management system that lets students file, track, and rate the resolution of concerns, while staff, deans, quality assurance officers, and administrators manage routing, response, and reporting across offices.
Student
Submit complaints, attach evidence, track status, rate resolutions
Staff
Receive assigned tickets, update status, communicate with students
Dean
Oversee office performance, reassign tickets, view analytics
Quality Assurance
Monitor SLA compliance, review feedback, generate reports
Admin
Manage users, offices, categories, routing & SLA rules
PROJECT SNAPSHOT
PLATFORM
Next.js web application
USER ROLES
5 (Student, Staff, Dean, QA, Admin)
CORE WORKFLOW
Submit → Route → Resolve → Rate
REPORTING CYCLE
Phase 6 — mid-development
CURRENT STATUS
50% of planned scope complete
ParSU e-Feedback System | Development Progress Report
3

## Slide 4
Progress at a Glance
Chart: 
| Completed | Remaining
Overall | 50 | 50
50%
OVERALL COMPLETE
COMPLETION BY MODULE
Student Portal
80%
Staff Workflow
70%
Dean Oversight
55%
QA & Analytics
40%
Admin Controls
45%
Notifications & Email
35%
Reporting Suite
25%
ParSU e-Feedback System | Development Progress Report
4

## Slide 5
What's Done — Core Platform
COMPLETED
Authentication & Access
Registration, login, password reset, and role-based routing for all five user types are working end to end.
Complaint Submission
Students can file complaints with category selection, descriptions, and file attachments through a guided form.
Complaint Tracking
Students and staff can view complaint lists, filter/sort, and open a detailed timeline of each ticket.
Staff Resolution Workflow
Staff can self-assign tickets, update statuses, add internal notes, and message students.
Role-Based Dashboards
Each role (Student, Staff, Dean, QA, Admin) has a working dashboard summarizing relevant activity.
Database & Data Model
Core schema for complaints, users, offices, categories, attachments, and audit logs is finalized (see ERD).
ParSU e-Feedback System | Development Progress Report
5

## Slide 6
What's Left — Remaining Work
IN PROGRESS
Analytics & Trend Reporting
40%
Charts for complaint trends and category/priority breakdowns are partially built; drilldowns still pending.
SLA Automation
45%
SLA rule configuration exists in the data model; automated breach detection and alerts are not yet wired up.
QA Feedback Review
30%
QA feedback listing page is scaffolded; scoring workflow and resolution-quality review are not implemented.
Admin Configuration Suite
50%
Offices, categories, and routing-rule screens exist but validation, bulk actions, and audit views need work.
Notifications & Email
40%
In-app notification panel is live; transactional email delivery and digesting are still being integrated.
Testing, Docs & Deployment
25%
Integration tests cover core flows only; production hardening and a deployment runbook remain.
ParSU e-Feedback System | Development Progress Report
6

## Slide 7
Technical Foundation
TECH STACK
•
Frontend: Next.js (App Router), React, Tailwind CSS
•
Backend: Next.js API routes, server-side services layer
•
Database: MongoDB with Mongoose data models
•
Auth: Session-based auth with role-based access control
•
Infra: Vercel deployment, scheduled cron for SLA checks
STATUS OF EACH LAYER
Data model
Stable
API routes
Core done, edge cases WIP
UI components
In progress
CORE DATA ENTITIES
User
Complaint
Office
Category
Attachment
AuditLog
Notification
GeneratedReport
Settings
Full entity-relationship diagram available in project documentation.
ParSU e-Feedback System | Development Progress Report
7

## Slide 8
Timeline & Next Steps
Phase 1–3
Planning, data model, auth & core UI
Complete
Phase 4–5
Student & staff complaint workflow
Complete
Phase 6 (current)
Dean/QA tooling, analytics, notifications
In progress — 50%
Phase 7
Admin configuration, SLA automation, full reporting
Upcoming
Phase 8
Testing hardening, UAT, deployment
Upcoming
IMMEDIATE NEXT STEPS
1. Finish SLA breach automation & alerts 2. Complete QA feedback scoring workflow 3. Wire up email notification delivery 4. Expand analytics drilldowns 5. Increase automated test coverage
ParSU e-Feedback System | Development Progress Report
8

## Slide 9
We're Halfway There
The core platform — authentication, complaint submission, and staff resolution — is live and working. The next phase focuses on analytics, automation, and reporting to bring ParSU e-Feedback to full completion.
Thank you
Questions & discussion welcome